EXECUTIVE SUMMARY

- Introduction

The City Government of Panabo, a third class component city in the Province of Davao del Norte was created on March 31, 2001 by virtue of Republic Act No. 9015. It has a total land area of 25,123 hectares, 78.76 percent of which is primarily agricultural. The City is comprised of forty (40) barangays with a total population of 184,599 based on the 2015 census by the Philippine Statistics Authority.

Having been identified as an area for agri-industrialization, the City serves as a gateway to the Province which is thirty-two (32) kilometers away from Davao City and twenty-eight (28) kilometers to Tagum City and is accessible by any means of transportation.

It is envisioned to be a progressive, ecologically balanced, and peaceful agri-industrial City characterized by a friendly, disciplined, empowered, and self-reliant citizenry led by efficient and effective political leaders under transparent governance with sufficient facilities and services as well as social justice and equality to all Panaboans.

The Commission has been implementing risk-based audit in the conduct of its audit services. However, to meet the evolving developments in public governance and fund management, the results-based approach in audit was incorporated. The integration of these approaches through the Financial Audit Manual were applied in the audit of the accounts and operations of the Local Government Unit (LGU).

A financial and compliance audit was conducted on the accounts and operations of Panabo City for CY 2022. The audit consisted of review of operating procedures, evaluation of the LGU’s programs and projects, interview of concerned government officials and employees, verification, reconciliation, and analysis of accounts, and such other procedures considered necessary.

- Financial Highlights

Financial Condition and Operation

The financial condition and performance of the City Government of Panabo for Calendar Year 2022 with comparative figures for CY 2021 are summarized as follows:

| Account Groups | 2022 | 2021 | Difference |  |
| --- | --- | --- | --- | --- |
|  |  |  | Increase (Decrease) |  |
|  |  |  | Amount | % |
| Assets | 5,176,841,983.35 | 4,183,070,288.90 | 993,771,694.45 | 23.76% |
| Liabilities | 1,606,113,633.53 | 1,156,013,872.51 | 450,099,761.02 | 38.94% |
| Equity | 3,570,728,349.82 | 3,027,056,416.39 | 543,671,933.43 | 17.96% |
| Revenue | 1,815,833,563.55 | 1,332,017,484.89 | 483,816,078.66 | 36.32% |
| Current Operating Expenses | 1,136,927,728.17 | 1,007,934,254.87 | 128,993,473.30 | 12.80% |
| Transfers and Subsidy From | 10,612,957.54 | 153,047,594.01 | (142,434,636.47) | (93.07%) |
| Transfers and Subsidy To | (21,104,847.27) | (55,694,875.47) | 34,590,028.20 | (62.11%) |
| Miscellaneous Income | 2,218,956.25 | 1,643,931.51 | 575,024.74 | 34.98% |
| Surplus (Deficit) for the period | 670,632,901.90 | 423,079,880.07 | 247,553,021.83 | 58.51% |

In CY 2022, the total assets of the LGU had increased by P993.772 million or 23.76% which is attributed mainly to the receipt of loan proceeds and additions in property, plant and equipment. The corresponding increase in liabilities by P450 million is mainly attributable to the recorded loans payable as well as the increase in deferred credits.

The increase in revenues by P483.816 million or 36.32% was derived from the increase in tax revenues, share from internal revenue collections, service and business income and grants and donations in cash. The increase in current operating expenses is primarily due to the increase in payment of personnel services and payment of interest.

Of the total realized revenue, P1.830 billion was used to fund the following expenditures appropriated for the City’s operation and the various programs and projects aligned for the year. Comparative information of current appropriations and its corresponding obligation for 2022 and 2021 are as follows:

| Expenditure | 2022 |  |  |
| --- | --- | --- | --- |
|  | Appropriations | Allotment | Obligation |
| Personal Services | 538,738,699.02 | 480,186,570.17 | 480,186,570.17 |
| Maintenance and Other Operating Expenses | 747,745,696.12 | 701,552,071.50 | 696,137,010.70 |
| Capital Outlay | 543,767,848.89 | 543,061,741.58 | 130,523,745.88 |
| Total | 1,830,252,244.03 | 1,724,800,383.25 | 1,306,847,326.75 |
|  | 2021 |  |  |
| Personal Services | 477,510,147.77 | 427,091,365.27 | 427,091,365.27 |
| Maintenance and Other Operating Expenses | 643,589,395.32 | 559,139,185.25 | 559,139,185.25 |
| Capital Outlay | 958,144,644.02 | 952,916,566.05 | 301,184,483.79 |
| Total | 2,079,244,187.11 | 1,939,147,116.57 | 1,287,415,034.31 |

- Auditor’s Opinion on the Financial Statements

The Auditor rendered a qualified opinion on the fairness of presentation of the financial position of the City Government of Panabo, Davao del Norte  as at  December 31, 2022, and its financial performance and cash flows for the year then ended due to erroneous/non recording of affected accounts totaling P 21,521,886.76,

- Summary of Significant Observations and Recommendations

Presented below are significant audit observations and corresponding recommendations, the details of which and the other audit observations are presented in Part II of this report:

- Underutilization of allotted funds totaling P415,712,134.30 and delay in the implementation of projects totalling P154,489,595.30 affects the efficiency and economy in the government operation and deprives the constituents of the expected benefits that could have been derived therefrom; while, unexpended balances totaling P5,080,330.04 of completed projects with continuing appropriation were not reverted to the unappropriated surplus which could have been utilized to fund other priority projects/programs/activities of the government.

We recommended the City Mayor to strengthen the preliminary engineering activities for the identified priority projects before its inclusion in the AIP/Annual Budget by hiring additional technical personnel to undertake the detailed engineering activities, facilitate the field survey and inspection and the preparation of program of works and design plans to ensure that the infrastructure projects are procurement-and-implementation ready by the time the budget become operative.

Also, we recommended to require the implementing offices to fast track the completion of all on-going projects under 20% Development Fund as at December 31, 2022 and impose liquidating damages and applicable legal actions against contractors with incurred significant delays.

Finally, we recommended the City Mayor to direct the:

- City Housing Section to conduct initial screening of the intents from landowners and identify the prospective properties for the Land Banking projects prior to its integration in the AIP/preparation of the budget under the 20% Development Fund to minimize the selection process and fast track the acquisition of lot for the housing projects;

- Implementing Offices concerned to Conduct evaluation on the unimplemented projects to determine whether it is still favourable on the part of the city government to continue the projects, otherwise, consider immediate realignment or reversion to the unappropriated surplus for re-appropriation subject to budgetary rules;

- City Budget Office to close and/or revert the unexpended continuing allotments of the completed projects to the unappropriated surplus pursuant to Section 322 of RA No. 7160; and

- Require the City Planning and Development Office to closely monitor and evaluate the status of the implementation of projects to facilitate the imposition of the proper course of action in the incurrence of delayed/unimplemented projects and to ensure timely completion thereof.

- The delayed project implementation and slow utilization of fund pertaining to the Funds received from Department of Budget and Management contravene the provisions of Presidential Decree No. 1445 and Local Budget Circular (LBC) No. 135 dated January 20, 2021, thus, affecting the City Government’s efficiency in delivering the timely and optimum benefits derived from the projects.

We recommended the City Mayor to direct the City Engineering Office to:

  - Submit the necessary documents (i.e. PAGASA certification, etc.) to support the justification of unfavorable weather conditions on various time extensions and suspension granted pertaining to the Upgrading of Local Access Road project at Brgy. Katualan;

  - Provide a written justification on the deficiencies noted on the issued Extension Orders for the Upgrading of Local Access Road project at Brgy. Kiotoy for further evaluation by the Audit Team;

  - Prepare the required PERT/CPM network of the project activities as an attachment to the POW and include an estimate on the rainy/unworkable days to arrive at a realistic basis of the total contract time of the project and avoid incurrence of unnecessary delays; and

  - Ensure that the grant of time extension and/or work suspension is thoroughly reviewed and supported with complete and sufficient documentation to prevent abuse by the contractors.

We further recommended to direct the City Planning and Development Office and concerned offices to closely monitor and evaluate the status of the implementation of projects to facilitate the imposition of the proper legal action against contractors with unjustified delays incurred.

- Summary of Suspensions, Disallowances and Charges as at Year-End

| NS/ND/NC | Balance as at Dec 31, 2021 | This Period (Jan 1 to Dec 31 2022) |  | Balance as at Dec 31, 2022 |
| --- | --- | --- | --- | --- |
|  |  | NS/ ND/ NC | NSSDC |  |
| Notice of Suspension | 5,706,288.00 | 0.00 | 5,706,288.00 | 0.00 |
| Notice of Disallowance | 8,685,626.52 | 0.00 | 795,407.91 | 7,890,218.61 |
| Notice of Charge | 0.00 | 0.00 | 0.00 | 0.00 |
| Total | 14,391,914.52 | 0.00 | 6,501,695.91 | 7,890,218.61 |

During the year, the Team issued Notice of Settlement of Suspension, Disallowances and Charges amounting to P6,501,695.91, leaving an outstanding balance of P7,890,218.61 as at December 31, 2022.

- Implementation of Prior Years’ Audit Recommendations

Of the ninety (90) audit recommendations embodied in CYs 2014 to 2021 Annual Audit Reports, forty-five (45) or 50% were implemented, while forty-five (45) or 50% remained not implemented. Of the forty-five (45) implemented recommendations, thirty-two (32) were reiterated/revised  in current year’s audit findings.